## Sheet1
ID | Assigned work | Executor | Estimated time |  |  | Reality |  |  | Desired results | Status | Extra Notes
|  |  | Begin | End | Hour | Begin | End | Hour
| Write test cases for the functions included in the Attachment screen | Le Cong Hoi | 2022-04-06 | 2022-04-07 | 5 | 2022-04-06 | 2022-04-07 | 5 | Complete the assigned tasks, write all the necessary test cases for the software at the Attachment screen | Complete | Right on schedule as planned
| Write test cases of the functions included in the Add defect screen | Nguyen Hoang Nhut Lam Phan Phuong Phat | 2022-04-06 | 2022-04-07 | 5 | 2022-04-06 | 2022-04-07 | 5 | Complete the assigned tasks, write all necessary test cases for the software at the Add Defect screen | Complete | Right on schedule as planned
| Write test cases for the functions included in the DefectViewOrEdit screen | Nguyen Hoang Nhut Lam Phan Phuong Phat Le Cong Hoi | 2022-04-13 | 2022-04-14 | 5 | 2022-04-13 | 2022-04-14 | 7 | Complete the assigned tasks, write all the necessary test cases for the software at the Defect View or Edit screen | Complete | Later than expected
| Write test cases for the functions included in the Defect List screen | Nguyen Hoang Nhut Lam Phan Phuong Phat Le Cong Hoi | 2022-04-13 | 2022-04-14 | 5 | 2022-04-13 | 2022-04-13 | 4 | Complete the assigned tasks, write all the necessary test cases for the software at the Defect List screen | Complete | Sooner than expected
| Write test cases for the functions included in the Batch Update screen | Nguyen Hoang Nhut Lam Phan Phuong Phat | 2022-04-20 | 2022-04-20 | 5 | 2022-04-20 | 2022-04-20 | 4 | Complete the assigned tasks, write all the necessary test cases for the software at the BatchUpdate screen | Complete | Sooner than expected
| Write test cases for the functions available in the Export Defect screen | Le Cong Hoi | 2022-04-20 | 2022-04-20 | 5 | 2022-04-20 | 2022-04-20 | 5 | Complete the assigned tasks, write all the necessary test cases for the software at the Export Defect screen | Complete | Right on schedule as planned